Greepam Project charter

1. Project purpose  
   EPAM has run its business in Kraków for several years now and it seems it is well established in this city. Local community problems affect also EPAM employees and air pollution is the most import problem these days. Although public transport is well developed in Kraków and city authorities invest a lot of effort and money in making it ecological, most of citizens choose to commute by car. Together with obsolete heating techniques it generates a lot of pollution and Kraków is highly ranked among most cities with highest pollution of the air. High pollution with particulates can cause diseases of respiratory, circulatory and nervous systems, affects peoples concentration and memory, cause depressions and overall bad state of being. Polluted air makes outdoor activities impossible for major part of the year, which is particularly unfavorable for those who work seated for most of the day. From a corporate point of view, high pollution is a deterring factor while efforts are made to move employees from other locations to Kraków.   
   Commuting by car not only pollutes the air but also makes it impossible to demarcate enough space on parking lots close to high density layout offices or utilize whatever is available in optimal manner. Greepam project intends to soften problem of high utilization of cars for daily commute on a company scale, by promoting ecological approach of reaching the office.
2. Detailed product description  
   Greepam project intends to deliver means (software) and methodology (business process) to optimize utilization of parking lot resources and fulfill corporate responsibility policies:
   * software deliverables shall include design and implementation i.e. coding and testing and deployment of web and mobile applications for all major mobile platforms. The mobile software shall have capability of determining how EPAM employee commutes by tracking and analyzing geospatial data. This is to be used for rewarding employees that commute to work by bike, walk, use public transportation or share seats in a car. Value of benefits will depend on kind of transportation (assuming walking and riding a bike being most valuable) and distance a person needs to cover. Also those who go to work by car will find the application useful as it will allow monitoring of space in car parks. Server side of the application together with web interface is intended to deliver detailed reports about utilization of parking spaces and listing employees that make use of alternatives to cars.
   * development of resource management practices for rewarding employees that make use of cars alternatives and adjusting number of parking spaces to actual needs
   * promo campaignto spread a good word in media about EPAM and its contribution to resolving local society problems.
3. Project objectives  
   There are two main objectives of Greepam project:
   * to strengthen EPAM image of socially responsible corporate that contributes to sustainable development of local society by promoting ecological means of transport
   * to optimize office resources in terms of parking space usage.
4. Project manager  
   Project Manager Bruce Spruce is hereby authorized to interface with management as required, negotiate for resources, manage all project tasks, scheduling, and communication to ensure successful and timely completion of the project. A project plan will be developed and submitted to the management team for approval. It will include: scope statement, schedule, cost estimate, draft of resource plan, quality, risk, procurement and stakeholder management as well as project control. Mr. Spruce is authorized to approve all budget expenditures up to, and including, the allocated budget amounts. All resources will be assigned by the project sponsor, Viktor Bondariev. Success will be determined by the Project Sponsor, Viktor Bondariev, who will also authorize completion of the project.

**Authorization  
Approved by the Project Sponsor:  
\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**Viktor Bondariev**