## Arkusz1
| Risk identification | Quantitive risk |  |  |  |  | Risk response
| Risk | Risk category | Probability 0-10 | Impact 0-10 | Risk score 0-100 | Risk ranking | Risk response | Trigger | Risk owner
1 | Legal
| No certified company car driver | Regulatory | 3 | 8 | 24 | 4 | Transfer | Preparation failure
| Lack of procedures for outdoor labour work | Governance | 3 | 3 | 9 | 10 | Contingency | Preparation failure
2 | Climate and outdoor condition
| Physical measurements delay due to bad weather | Operational | 8 | 4 | 32 | 2 | Contingency | Force majeure
3 | Accidents
| Road accidents and damage of equipement | Operational | 2 | 8 | 16 | 7 | Transfer | Accident
| Accidental body hurts during physical measurements | Operational | 1 | 8 | 8 | 12 | Accept | Accident
4 | Technical issues
| No expertise in physical measurements | Governance | 3 | 8 | 24 | 4 | Transfer | Lack of knowledge
| Hardware failures | Operational | 1 | 5 | 5 | 14 | Contingency | Accident
| Delays due to unpredictable activities | Operational | 3 | 3 | 9 | 10 | Contingency | Lack of knowledge
5 | External data access
| Fail to find precise city maps | Strategic | 1 | 3 | 3 | 15 | Accept | Wrong assumptions
| Fail to find reliable public transportation schedules | Strategic | 3 | 3 | 9 | 10 | Accept | Wrong assumptions
6 | Property management agreement
| No agreement on sharing parking lot data | Strategic | 2 | 3 | 6 | 13 | Accept | Wrong assumptions
7 | Staffing
| Specialists move to higher priority project | People | 3 | 5 | 15 | 8 | Escalate | Organization
| Specialists work inefficiently due to partial involvement | People | 2 | 5 | 10 | 9 | Mitigate | Organization
| Budget decreased due to higher priority projects | Financial | 2 | 5 | 10 | 9 | Contingency | Organization
8 | Success of campaign and software
| High demand for releasing application publicly | Strategic | 4 | 4 | 16 | 7 | Exploit | Project success
| Ideas for employees tracking utilization | Governance | 3 | 6 | 18 | 6 | Exploit | Project success
| Savings made on parking lot rent | Financial | 5 | 5 | 25 | 3 | Exploit | Project success
| High visibility of EPAM in media | Strategic | 5 | 7 | 35 | 1 | Exploit | Project success