## RACI Charts
Steps will be highlighted if A and R are not assigned.
[7 empty] | R: | Does the step
RACI Chart | [6 empty] | A: | Accountable for the step
[7 empty] | C: | Consulted with before the step
[7 empty] | I: | Informed when the step is completed
|  | Project: | Greepam
| MILESTONE | STEP | DESCRIPTION | Initiator 1 | Initiator 2 | Initiator 3 | Project Manager | Architect | UX Designer | Development Team Lead | Backend Developer | Web Developer | Mobile Developer | Quality Assurance 1 | Quality Assurance 2 | Public Relations
| Project Start | 1 | Prepare outcome description | A/R | I/C | I/C
|  | 2 | Prepare demo screens | I/C | A/R | I/C
|  | 3 | Prepare plan, resources and budget estimation | I/C | I/C | A/R
|  | 4 | Prepare presentation for the Management | A/R | R | R
|  | 5 | Approval from EPAM Management | R | A/R | R
| Initiation | 6 | Ensure Project Manager | A/R | I/C | I/C | I
|  | 7 | Ensure developers and testers | I/C | I/C | I/C | A/R | I | I | I | I | I | I | I | I
|  | 8 | Ensure hardware, software, testing tols | I/C | I/C | I/C | A/R | I | I | I | I | I | I | I | I
|  | 9 | Ensure PR availability | I | A/R | I | [9 empty] | I/C
|  | 10 | Ensure office space | I | I | A/R | I/C | I | I | I | I | I | I | I | I
| Initial Design | 11 | Gather information about public transport | A/R | I | I | I | I | I
|  | 12 | Gather information about parking places | I | A/R | I | I | I | I
|  | 13 | Research software physics | I | I | I | I | A/R |  | R | I | I | I
|  | 14 | Research external API for software solution | I | I | I | I | A/R |  | R | I | I | I
|  | 15 | Prepare with PR benefits policy | I | I | A/R | I | I | I | [6 empty] | R
|  | 16 | Design software architecture | I/C | I/C | I/C | I | A/R |  | I/C | I | I | I | I | I
|  | 17 | Design UX and GUI mobile and web look | I/C | I/C | I/C | I | A/R |  | I/C | I | I | I | I | I
|  | 18 | Plan software milestones and tests | I/C | I/C | I/C | A/R | R |  | R | I | I | I | I | I
| Software Implementation | 19 | Project Management | I | I | I | A/R
|  | 20 | Iterative backend implementation | I | I | I | A | C |  | R | R | I | I | I | I
|  | 21 | Iterative GUI implementation | I | I | I | A | C | C | I | I | R | R | I | I
|  | 22 | Initial user tests of all use cases | I | I | I | I |  |  | I | I | I | I | A/R | R
| Full and stable | 23 | Ensure software stability on various platforms | I | I | I | A |  |  | R | C | C | C | C
|  | 24 | Fixing bugs found in tests | I | I | I | A | C |  | R | R | R | R | R | I | I
|  | 25 | End user prototype tests | I | I | I | A |  |  | R |  |  | R | R | I | I
|  | 26 | Deploy stable software version | I | I | I | A | C |  | R |  | R | I | I
| Releasing and campaign | 27 | Organize promotion campaign in EPAM | I: C; I: C; I: A/R | R
|  | 28 | Organize opening party in EPAM | I: A/R; I: C; I: C | R
|  | 29 | Organize public campaign in media (social media, local newspapers) | I: C; I: A/R; I: C | R
|  | 30 | Project Management | I | I | I | A/R |  |  | I/C | I/C | I/C | I/C | I/C | I/C
|  | 31 | Software support | I | I | I | A |  |  | R | R | R | R | R | R
| Research and observations | 32 | Award users | I: C; I: A/R; I: R | R
|  | 33 | Optimize usage of parking spaces | I: A/R; I: I/C; I: I/C | I/C
|  | 34 | Research employees commuting habits | I: I/; I: I/C; I: A/R | I/C
|  | 35 | Find out usage of tracking employees | I: R; I: R; I: A/R | I/C
|  | 36 | Organize employees feedback (surveys) | A/R | I/C | I/C | I | I | I | I | I | I | I | I | I | R
|  | 37 | Prepare presentation about results | R | A/R | R | I | I | I | I | I | I | I | I | I | I/C
|  | 38 | Present results and futher ideas to the Management | R A/R R: A/R; R I/C A/R: R; A/R I/C R: R; I/C R I/C: I